[ COMPANY LOGO ]

CONSTRUCTION BID TEMPLATE

COMPREHENSIVE TENDER / BID PROPOSAL TEMPLATE — INDIA

Reusable for Government & Private Projects — Residential | Commercial | Institutional | Infrastructure

| Field | Details |
| --- | --- |
| Project Title | [Project Name] |
| Project Location | [Site Address / City / State], India |
| Client / Employer | [Client Name] |
| NIT / Tender Reference No. | [NIT / Tender Ref. No.] |
| Bid Submission Date & Time | [Date, Time] |
| Bid Opening Date & Time | [Date, Time] |
| Bid Validity Period | [XX] days from the bid due date |
| Submitted By | [Your Company Name] |
| Registered Office Address | [Company Address] |
| GSTIN / PAN | [GSTIN] / [PAN] |
| Contact Person, Phone & Email | [Name, Phone, Email] |

### Authorized Signatory Block

| Name | Designation | Signature | Date | Company Seal |
| --- | --- | --- | --- | --- |
| [Name] | [Designation] | ___________ | [Date] | [SEAL] |

How to use this section: Replace every bracketed [placeholder] with actual project details before issuing this document. The cover page should mirror the exact project title and NIT/tender reference used by the Employer/Client to avoid a technical rejection for mismatched identification.

# Table of Contents

1.  Cover Page

2.  Instructions & Compliance Checklist

3.  Scope of Work

4.  Bill of Quantities (BOQ) / Price Schedule

5.  Rate Analysis & Cost Breakdown (Internal Use)

6.  Project Schedule & Method Statement

7.  Company Profile & Credentials

8.  Statutory & Compliance Documents Checklist

9.  Commercial Terms & Conditions

10.  Signatures & Declarations

11.  Excel / Google Sheets Implementation Notes

Appendix A — Glossary of Common Indian Tendering Terms

Appendix B — Typical Employers / Authorities in the Indian Market

Appendix C — Common Disqualification Reasons in Indian Tenders

# 2.  Instructions & Compliance Checklist

Most Indian tenders — government (CPWD, State PWD, NHAI, Metro Rail Corporations, Smart City SPVs, municipal bodies) and increasingly large private developers — follow a two-envelope (or two-cover / two-bid) system: a Technical Bid (Envelope/Cover I) containing eligibility, experience, and compliance documents, and a Financial Bid (Envelope/Cover II) containing the priced BOQ. The Financial Bid of a bidder is opened only if the Technical Bid is found responsive. Use the checklist below before every submission.

## 2.1  Two-Envelope System — What Goes Where

| Envelope | Typical Contents |
| --- | --- |
| Envelope I — Technical Bid / Cover I | EMD/Bid Security instrument, tender fee receipt, eligibility & experience documents, statutory registrations (GST/PAN/MSME), key personnel CVs, machinery list, undertakings/affidavits, technical proposal, signed drawings & specifications (if required), Power of Attorney |
| Envelope II — Financial Bid / Cover II | Priced Bill of Quantities (BOQ), covering letter, price breakup (if asked), rate justification for abnormally low/high rates (if raised by TEC) |
| Outer Envelope | Both sealed envelopes placed inside one outer envelope/cover, super-scribed with NIT number, project name, and 'DO NOT OPEN BEFORE [date/time]' |

## 2.2  Pre-Submission Compliance Checklist

| # | Item | Complied (Y/N) | Remarks |
| --- | --- | --- | --- |
| 1 | NIT / tender document downloaded and fully reviewed |  |  |
| 2 | All addenda / corrigenda issued by the Employer incorporated |  |  |
| 3 | Two-envelope system followed — Technical & Financial bids sealed separately |  |  |
| 4 | EMD / Bid Security enclosed in the correct instrument & amount (DD / BG / online) |  |  |
| 5 | Tender document fee paid (if applicable) and receipt attached |  |  |
| 6 | Statutory documents attached — GST, PAN, MSME/Udyam, EPF, ESIC, Labour License |  |  |
| 7 | Drawings, specifications and BOQ reviewed, signed/stamped as required |  |  |
| 8 | Site visit undertaken and site visit certificate obtained (if mandated) |  |  |
| 9 | Pre-bid meeting minutes and query clarifications incorporated into the bid |  |  |
| 10 | Bid validity period accepted and stated correctly in the bid letter |  |  |
| 11 | Power of Attorney / Board Resolution authorizing the signatory enclosed |  |  |
| 12 | Bid submitted in the correct format — physical cover(s) or e-tender portal upload |  |  |
| 13 | Documents self-attested / notarized / attested by Gazetted Officer as required |  |  |
| 14 | Non-blacklisting affidavit and Integrity Pact signed (for eligible govt. tenders) |  |  |
| 15 | Financial bid figures cross-checked — no arithmetic mismatch between rate × qty = amount |  |  |

How to use this section: A junior estimator should complete this checklist item-by-item at least 24 hours before the submission deadline, not the morning of. In Indian e-tendering (GeM, CPPP, state e-procurement portals), uploads can fail close to the deadline due to portal congestion or DSC (Digital Signature Certificate) token issues — build in buffer time.

# 3.  Scope of Work

This section defines precisely what the bid price includes, what it excludes, and the assumptions underlying the price — the single most common source of post-award disputes in Indian contracting is an ambiguous or assumed scope.

## 3.1  General Description

[Insert a 2-4 paragraph narrative description of the project: type of structure (e.g., G+4 residential apartment / warehouse / hospital / road package), location, plot/site area, built-up area, structural system, key project milestones, and the specific package being bid (e.g., 'Civil + Finishing works only' or 'Turnkey civil, structural and MEP').]

## 3.2  Inclusions, Exclusions & Assumptions

| Category | Details |
| --- | --- |
| Inclusions | [e.g., All civil, structural and finishing works as per drawings & BOQ; testing & commissioning of MEP systems; statutory approvals liaison support; safety, security and housekeeping during construction; as-built drawings on completion] |
| Exclusions | [e.g., Cost of land; statutory development charges/premiums payable to the local authority; furniture, fixtures & loose equipment (FF&E); landscaping beyond the scope shown in drawings; utility deposit/connection charges payable to DISCOM/Water Board; GST (shown separately per Commercial Terms)] |
| Assumptions | [e.g., Soil bearing capacity per the geotechnical report provided by the Employer; uninterrupted site access and power/water supply from day one; no rock excavation unless specifically billed; work in single shift unless accelerated scope is agreed] |

## 3.3  Trade-Wise Scope of Work

### Civil / Structural

- Earthwork, excavation, backfilling and soil treatment

- PCC, RCC (foundation, columns, beams, slabs, staircase)

- Reinforcement steel and formwork/shuttering

- Masonry — brick/block work, plastering

### Finishes

- Flooring, tiling, cladding and stone work

- Doors, windows, glazing and hardware

- Painting, waterproofing and false ceiling

- External development — compound wall, paving, landscaping

### MEP (if included in this bid package)

- Electrical — internal wiring, DBs, lighting, earthing, DG/solar provision

- Plumbing & sanitary — water supply, drainage, sanitary fixtures, STP/WTP if applicable

- Fire fighting & fire detection (as required by NBC 2016 / local fire NOC authority)

- HVAC / mechanical ventilation (where applicable to project type)

How to use this section: Mirror the Employer's own scope divisions and terminology from the NIT wherever the tender prescribes them — do not invent your own trade breakdown for a government tender where the BOQ structure is fixed. For private/negotiated bids, this trade-wise breakdown can be adapted freely to match the project type.

# 4.  Bill of Quantities (BOQ) / Price Schedule

The BOQ is the priced Schedule of Quantities forming the Financial Bid. Amount is always Quantity × Unit Rate — never entered as an independent figure. Where the Employer has issued a BOQ in a fixed format (typical of CPWD, PWD, NHAI, Metro, and Smart City tenders), that exact item numbering, description, unit and quantity must be reproduced without alteration; the bidder only fills in the Unit Rate and the resulting Amount column.

## 4.1  Sample BOQ Structure

### A.  Civil Works

| Item No. | Description | Unit | Quantity | Unit Rate (₹) | Amount (₹) |
| --- | --- | --- | --- | --- | --- |
| A.1 | Excavation in ordinary soil for foundation, up to 1.5m depth | Cum | [Qty] | [Rate] | [Qty × Rate] |
| A.2 | PCC 1:4:8 below foundation | Cum | [Qty] | [Rate] | [Qty × Rate] |
| A.3 | RCC M25 in columns, beams & slabs complete (excl. reinforcement) | Cum | [Qty] | [Rate] | [Qty × Rate] |
| A.4 | TMT reinforcement steel Fe500D, cutting, bending & placing | Kg | [Qty] | [Rate] | [Qty × Rate] |
| A.5 | Brick/AAC block masonry in CM 1:6 | Cum | [Qty] | [Rate] | [Qty × Rate] |

Sub-Total — Civil Works (A)

### B.  Finishes

| Item No. | Description | Unit | Quantity | Unit Rate (₹) | Amount (₹) |
| --- | --- | --- | --- | --- | --- |
| B.1 | Vitrified tile flooring 600x600mm | Sqm | [Qty] | [Rate] | [Qty × Rate] |
| B.2 | Internal plastering, CM 1:6, 12mm | Sqm | [Qty] | [Rate] | [Qty × Rate] |
| B.3 | Interior emulsion paint, 2 coats over primer | Sqm | [Qty] | [Rate] | [Qty × Rate] |
| B.4 | UPVC / aluminium windows with glazing | Sqm | [Qty] | [Rate] | [Qty × Rate] |

Sub-Total — Finishes (B)

### C.  MEP (Mechanical, Electrical & Plumbing)

| Item No. | Description | Unit | Quantity | Unit Rate (₹) | Amount (₹) |
| --- | --- | --- | --- | --- | --- |
| C.1 | Concealed wiring, PVC conduit with FRLS copper cable, light point | Point | [Qty] | [Rate] | [Qty × Rate] |
| C.2 | CPVC piping for internal water supply | Rmt | [Qty] | [Rate] | [Qty × Rate] |
| C.3 | Sanitary fixtures — WC (EWC with flush tank) | Nos | [Qty] | [Rate] | [Qty × Rate] |
| C.4 | Fire extinguishers, portable ABC type | Nos | [Qty] | [Rate] | [Qty × Rate] |

Sub-Total — MEP (C)

### D.  Provisional Items / Prime Cost (PC) Sums

| Item No. | Description | Unit | Quantity | Unit Rate (₹) | Amount (₹) |
| --- | --- | --- | --- | --- | --- |
| D.1 | Provisional sum for unforeseen ground conditions (rock excavation, if encountered) | Ls | 1 | [Rate] | [Amount] |
| D.2 | PC sum for Employer-nominated specialist works (e.g., elevator, solar PV) | Ls | 1 | [Rate] | [Amount] |
| D.3 | Contingency sum (as prescribed by the Employer, typically 2-5%) | Ls | 1 | [Rate] | [Amount] |

Sub-Total — Provisional Items (D)

### Grand Summary

| Description | Amount (₹) |
| --- | --- |
| Sub-Total — Civil Works (A) | [Amount] |
| Sub-Total — Finishes (B) | [Amount] |
| Sub-Total — MEP (C) | [Amount] |
| Sub-Total — Provisional Items (D) | [Amount] |
| TOTAL BID PRICE (A+B+C+D), excl. GST | [Amount] |
| Add: GST @ [applicable rate]% | [Amount] |
| GRAND TOTAL BID PRICE, incl. GST | [Amount] |

How to use this section: For government and most institutional/infrastructure tenders, do NOT change the item structure, numbering, description, unit, or quantity supplied in the Employer's BOQ — altering these is a common ground for technical rejection. Only the Unit Rate (and the computed Amount) should be entered by the bidder. For private/negotiated projects where you are building your own BOQ from drawings, keep item descriptions unambiguous and measurable per IS 1200 conventions so that variations can be priced against the same basis later.

# 5.  Rate Analysis & Cost Breakdown  (Internal Use — Not for Client Submission)

Every unit rate quoted in the BOQ should be traceable to a rate analysis — this is the estimator's internal working paper, never shared with the Employer, that justifies the price and protects the bidder if rates are later questioned by a Tender Evaluation Committee (TEC) for being abnormally high or low.

## 5.1  Components of a Rate Analysis

| Component | What to Include |
| --- | --- |
| Material Cost | Basic/ex-factory or landed material price + freight + loading/unloading, uplifted by a wastage/breakage allowance (typically 2-3% for steel, 5-8% for bricks/blocks, 5-10% for tiles/board materials, higher for irregular-shaped stone) |
| Labour Cost | Skilled (mason, carpenter, fitter, electrician) and unskilled (helper/coolie) man-day rates, applied against a realistic productivity/output norm for the item (e.g., cum of brickwork per mason-day) — reference CPWD/State PWD Standard Data Book output norms where available |
| Equipment & Plant (T&P) | Owned or hired plant/machinery cost (excavator, concrete pump, tower crane, mixer, vibrator) allocated per unit of work, including fuel/operator cost and standing charges during idle periods |
| Sub-Contractor Cost | Where a trade is sub-let (e.g., false ceiling, waterproofing, elevator), the sub-contractor's quoted rate plus the main contractor's coordination/supervision markup |
| Overheads | Site overheads (site staff, site office, temporary utilities, insurance) and head-office overheads, typically expressed as a % of direct cost (commonly 8-15% depending on project size and duration) |
| Contingency | A risk buffer for estimation uncertainty, typically 2-5%, distinct from any Employer-prescribed provisional/contingency BOQ item |
| Profit | The contractor's target margin, typically 5-12% depending on project risk profile and market competitiveness |

## 5.2  Sample Rate Analysis — RCC M25 in Columns/Beams/Slabs (per Cum)

| Description | Unit | Qty/Cum | Rate (₹) | Amount (₹) |
| --- | --- | --- | --- | --- |
| Cement (OPC 43/53 grade) | Bag | 8.0 | 380 | 3,040 |
| Coarse aggregate (20mm & 10mm down) | Cum | 0.90 | 1,650 | 1,485 |
| Fine aggregate (river/M-sand) | Cum | 0.45 | 1,950 | 878 |
| Water | Litre | 180 | 0.15 | 27 |
| Admixture (plasticizer) | Kg | 2.5 | 95 | 238 |
| Material Sub-Total (incl. 2% wastage) |  |  |  | 5,782 |
| Skilled labour (mason/carpenter) | Man-day | 0.35 | 950 | 333 |
| Unskilled labour (helper) | Man-day | 1.1 | 550 | 605 |
| Labour Sub-Total |  |  |  | 938 |
| Concrete pump / mixer / vibrator (T&P) | Cum | 1 | 420 | 420 |
| Equipment Sub-Total |  |  |  | 420 |
| Direct Cost Sub-Total (Material + Labour + Equipment) |  |  |  | 7,140 |
| Add: Contractor's Overheads @ 10% |  |  |  | 714 |
| Add: Contingency @ 3% |  |  |  | 236 |
| Add: Profit @ 8% |  |  |  | 651 |
| ANALYZED RATE PER CUM (rounded) |  |  |  | 8,741 |

How to use this section: Keep one such rate analysis sheet per BOQ item family (concrete grades, masonry types, flooring types, MEP points) rather than per individual line item — most Indian estimators maintain a master rate-analysis library that is refreshed quarterly for material price movements (cement, steel and diesel are the most volatile) and reused across tenders. This sheet is strictly internal — never attach it to the Financial Bid submitted to the Employer.

# 6.  Project Schedule & Method Statement

## 6.1  Sample Milestone Schedule

| Activity | Duration | Start | Finish |
| --- | --- | --- | --- |
| Mobilization & site establishment | [X] weeks | [Date] | [Date] |
| Excavation & foundation works | [X] weeks | [Date] | [Date] |
| RCC structure — ground floor to roof | [X] weeks | [Date] | [Date] |
| Masonry & plastering | [X] weeks | [Date] | [Date] |
| MEP first-fix (conduiting, piping) | [X] weeks | [Date] | [Date] |
| Flooring, tiling & finishes | [X] weeks | [Date] | [Date] |
| MEP second-fix, testing & commissioning | [X] weeks | [Date] | [Date] |
| Painting, external development & handover | [X] weeks | [Date] | [Date] |
| Defects Liability Period (DLP) commences | [X] months | [Date] | [Date] |

## 6.2  Sample Method Statements

### Excavation

Excavation to be carried out mechanically (excavator/JCB) to within 150mm of formation level, with final trimming done manually to avoid over-excavation and disturbance of the founding strata. Dewatering pumps to be kept on standby where the water table is encountered. Excavated earth suitable for backfill to be stockpiled separately from surplus material marked for disposal. Safety barricading and warning signage to be maintained around all open excavations.

### Concreting

Concrete to be batched at an on-site/RMC batching plant with mix design verified by trial cubes prior to the first pour of each grade. Placement by pump/chute with mechanical vibration (needle vibrators) to achieve full compaction without segregation. Cube samples to be taken per IS 456 sampling frequency for 7-day and 28-day strength testing. Curing to commence within 2 hours of final set and continue for a minimum of 7 days (moist hessian/curing compound).

### Brickwork / Block Work

Masonry units to be soaked in water for a minimum of 2 hours (bricks) prior to laying. Courses to be laid plumb and in level with a maximum lift of 1.2m per day to avoid mortar joint settlement. Vertical reinforcement/seismic bands to be provided at every [X]m height per the structural drawings. Raking of joints to be done as work proceeds to key the subsequent plaster coat.

### Finishes

Flooring/tiling to commence only after all overhead MEP first-fix and plastering in the area is complete and cured. Tile laying to maintain uniform joint width with spacers, checked for level and hollowness before grouting. Painting to follow the sequence: putty → primer → two coats of finish, with a minimum 24-hour drying interval between coats.

How to use this section: For larger tenders (typically above ₹5-10 crore, or any NHAI/Metro/Smart City infrastructure package), expand this milestone table into a full PERT/CPM network schedule in MS Project or Primavera P6, showing activity dependencies, the critical path, and resource loading — many government tenders mandate submission of a bar chart or network diagram as part of the Technical Bid.

# 7.  Company Profile & Credentials

## 7.1  Company Details

| Field | Details |
| --- | --- |
| Company / Firm Name | [Your Company] |
| Constitution | [Proprietorship / Partnership / LLP / Pvt. Ltd. / Public Ltd.] |
| Year of Incorporation / Establishment | [Year] |
| PAN | [PAN Number] |
| GSTIN | [GSTIN] |
| MSME / Udyam Registration No. | [Udyam Registration No.] |
| Contractor Class / License (if applicable) | [e.g., CPWD Class –I / State PWD Class-A] |
| Registered Office Address | [Address] |
| ISO Certifications (if any) | [ISO 9001 / 14001 / 45001 Certificate No.] |

## 7.2  Turnover & Net Worth (Last 3 Financial Years)

| Financial Year | Annual Turnover (₹) | Net Worth (₹) | Auditor's Certificate Ref. |
| --- | --- | --- | --- |
| [FY 2023-24] | [Amount] | [Amount] | [CA Certificate No.] |
| [FY 2022-23] | [Amount] | [Amount] | [CA Certificate No.] |
| [FY 2021-22] | [Amount] | [Amount] | [CA Certificate No.] |

## 7.3  Similar Completed Projects

| Client | Scope of Work | Contract Value (₹) | Completion Year | Completion Certificate Ref. |
| --- | --- | --- | --- | --- |
| [Client Name] | [e.g., G+4 residential, 45,000 sqft, civil + finishing] | [Amount] | [Year] | [Certificate No.] |
| [Client Name] | [Scope] | [Amount] | [Year] | [Certificate No.] |
| [Client Name] | [Scope] | [Amount] | [Year] | [Certificate No.] |

## 7.4  Key Personnel Proposed for This Project

| Name | Role | Qualification | Years of Experience |
| --- | --- | --- | --- |
| [Name] | Project Manager | [B.E./B.Tech Civil] | [X years] |
| [Name] | Site Engineer | [Diploma/B.E. Civil] | [X years] |
| [Name] | MEP Engineer | [B.E. Electrical/Mechanical] | [X years] |
| [Name] | Safety Officer | [Diploma in Industrial Safety] | [X years] |
| [Name] | Quantity Surveyor / Estimator | [B.E./Diploma Civil] | [X years] |

## 7.5  Machinery & Equipment Available for This Project

| Equipment | Capacity / Type | Owned / Hired | Quantity |
| --- | --- | --- | --- |
| Excavator | [e.g., JCB 3DX] | [Owned/Hired] | [Nos] |
| Concrete Pump | [e.g., 30 cum/hr] | [Owned/Hired] | [Nos] |
| Tower Crane | [Capacity] | [Owned/Hired] | [Nos] |
| Transit Mixer | [Capacity] | [Owned/Hired] | [Nos] |
| DG Set (standby power) | [kVA rating] | [Owned/Hired] | [Nos] |
| Scaffolding / Shuttering System | [System type] | [Owned/Hired] | [Sqm] |

How to use this section: Government tenders (CPWD/PWD/NHAI/Metro) typically prescribe minimum eligibility criteria for average annual turnover, similar-work experience value, and net worth — verify these against the specific NIT clause before relying on this profile, as falling short on any one criterion results in outright technical disqualification regardless of price competitiveness.

# 8.  Statutory & Compliance Documents Checklist

Compile every document below into the Technical Bid folder in this order; most e-procurement portals (GeM, CPPP, state portals) require each to be uploaded as a separately named PDF.

| Document | Required (Y/N) | Attached (Y/N) | Remarks |
| --- | --- | --- | --- |
| GST Registration Certificate |  |  |  |
| PAN Card (Company/Firm) |  |  |  |
| MSME / Udyam Registration Certificate |  |  |  |
| EPF (Employees' Provident Fund) Registration |  |  |  |
| ESIC (Employees' State Insurance) Registration |  |  |  |
| Labour License (under Contract Labour Act) |  |  |  |
| Income Tax Returns — last 3 years / CA-certified financials |  |  |  |
| Audited Balance Sheet & Profit and Loss — last 3 years |  |  |  |
| Non-Blacklisting / Non-Debarment Affidavit |  |  |  |
| Integrity Pact (for eligible large government tenders) |  |  |  |
| EMD / Bid Security instrument (DD / Bank Guarantee / Online receipt) |  |  |  |
| Bank Solvency Certificate |  |  |  |
| Work Completion Certificates (from clients listed in Section 7.3) |  |  |  |
| Power of Attorney authorizing the signatory |  |  |  |
| Partnership Deed / MOA & AOA (as applicable to constitution) |  |  |  |
| Experience Certificates for similar works |  |  |  |
| Safety Policy / EHS Certificate (e.g., ISO 45001) |  |  |  |
| Quality Management Certificate (e.g., ISO 9001) |  |  |  |
| Insurance Proof — Contractor's All Risk (CAR) & Workmen's Compensation |  |  |  |
| Any other document specifically listed in the NIT |  |  |  |

How to use this section: Cross-check this list against the exact 'Eligibility Criteria' and 'Documents to be Submitted' clauses of the specific NIT — the list above is a general-purpose superset; individual tenders commonly drop some items and add others (e.g., a Registration with a specific department, a caste/category certificate for reserved tenders, or a local-area preference certificate).

# 9.  Commercial Terms & Conditions

The clauses below are sample commercial terms suitable for a private/negotiated contract. For government tenders, these are largely superseded by the Employer's own General Conditions of Contract (GCC) and Special Conditions of Contract (SCC) — use this section instead as a checklist to confirm the bidder's acceptance of, or any deviations from, those GCC/SCC clauses.

## 9.1  Payment Terms

- Progress payments against monthly Running Account (RA) Bills / IPCs (Interim Payment Certificates), measured and certified by the Employer's engineer/consultant.

- Retention: [5-10]% of each RA bill withheld, released [50% on completion / 50% after the Defects Liability Period], or replaced by a Bank Guarantee at the contractor's option.

- Payment cycle: RA bills to be certified within [7-14] days of submission and paid within [21-30] days of certification.

- Mobilization advance (if any): [X]% of contract value against a Bank Guarantee, recovered proportionately from subsequent RA bills.

## 9.2  Variation / Change Order Process

- Any variation in scope, quantity, or specification to be instructed in writing by the Employer/Engineer via a Variation Order (VO) or Change Order before execution.

- Rates for varied items to be derived, in order of preference: (a) at the rates quoted in the BOQ for identical/similar items, (b) at a pro-rata rate derived from the BOQ, or (c) by fresh rate analysis mutually agreed, marked up by the same overhead/profit percentage embedded in the original bid.

- No payment for variations executed without a written instruction, except in a documented emergency/safety situation.

## 9.3  Time Extension Conditions

- Extension of Time (EOT) to be granted, without levy of liquidated damages, for delays attributable to the Employer (late drawings, site handover delay, payment delay) or force majeure events (per the force majeure clause).

- EOT claims to be submitted within [14] days of the delay event, with supporting programme impact analysis.

- Liquidated Damages (LD) for contractor-caused delay, if applicable, to be capped at [5-10]% of contract value.

## 9.4  Dispute Resolution

- Parties to first attempt amicable settlement through good-faith negotiation between authorized representatives.

- Unresolved disputes to be referred to arbitration under the Arbitration and Conciliation Act, 1996 (as amended), by a sole arbitrator appointed by mutual consent, or per the Employer's standard SCC clause for government contracts.

- Governing law: laws of India; seat and venue of arbitration: [City], [State]; language: English.

How to use this section: For CPWD/PWD/NHAI and similar government works, replace this entire section's operative clauses with an explicit statement of acceptance of the published GCC/SCC, listing only the bidder's formally permitted deviations (if the tender allows deviations at all — many do not). Silent or contradictory commercial terms in a government Technical Bid are a common ground for rejection.

# 10.  Signatures & Declarations

We, the undersigned, hereby declare that all information, documents, rates and representations furnished in this bid are true and correct to the best of our knowledge and belief. We confirm that we have read, understood and unconditionally accept the terms and conditions of the NIT/ tender document referenced on the cover page, including all addenda and corrigenda issued. We further declare that our firm has not been blacklisted or debarred by any Central/State Government department, public sector undertaking, or statutory authority in India as on the date of this bid, and that this bid is submitted without any collusion, comparison of figures, or arrangement with any other bidder.

| Name | Designation | Signature | Date |
| --- | --- | --- | --- |
| [Name] | [Designation] | ___________________ | [Date] |

Company Seal:  [SEAL]

# 11.  Excel / Google Sheets Implementation Notes

This document template is designed to convert cleanly into a working Excel or Google Sheets workbook. The mapping below shows one sheet per major section, which sheets should go into the Technical Bid vs. remain strictly internal, and the core formulas to wire up.

## 11.1  Suggested Sheet Structure

| Sheet Name | Maps to Document Section | Client-Facing? |
| --- | --- | --- |
| Cover | 1. Cover Page | Yes — submit |
| Compliance Checklist | 2. Instructions & Compliance Checklist | Internal only |
| Scope of Work | 3. Scope of Work | Yes — submit |
| BOQ - Civil | 4. BOQ — Section A | Yes — submit (Financial Bid) |
| BOQ - Finishes | 4. BOQ — Section B | Yes — submit (Financial Bid) |
| BOQ - MEP | 4. BOQ — Section C | Yes — submit (Financial Bid) |
| BOQ - Provisional | 4. BOQ — Section D | Yes — submit (Financial Bid) |
| BOQ Summary | 4. Grand Summary | Yes — submit (Financial Bid) |
| Rate Analysis | 5. Rate Analysis & Cost Breakdown | Internal only — NEVER submit |
| Schedule | 6. Project Schedule & Method Statement | Yes — submit (Technical Bid) |
| Company Profile | 7. Company Profile & Credentials | Yes — submit (Technical Bid) |
| Statutory Checklist | 8. Statutory & Compliance Documents Checklist | Internal only (tracking tool) |
| Commercial Terms | 9. Commercial Terms & Conditions | Yes — submit (private bids) / reference (govt.) |
| Declarations | 10. Signatures & Declarations | Yes — submit (Technical Bid) |

## 11.2  Client-Facing vs Internal — Rule of Thumb

- Client-facing sheets (Cover, Scope, BOQ tabs, Schedule, Company Profile, Declarations) should contain ONLY the information the Employer is entitled to see — no cost build-up, no margin, no internal notes.

- The Rate Analysis sheet must never be exported or printed alongside the submission bundle — keep it in a separate internal workbook, or password-protect/hide the sheet if it must remain in the same file.

- The Compliance Checklist and Statutory Checklist sheets are working tools for the bid team and are not part of the submission itself, even though the documents they track ARE submitted individually.

## 11.3  Suggested Formulas

### BOQ Tabs (Civil / Finishes / MEP / Provisional)

- Amount column: = Quantity × Unit Rate, e.g. =D5*E5 where D is Quantity and E is Unit Rate.

- Section sub-total: =SUM() over the Amount column range for that section, e.g. =SUM(F5:F9).

### BOQ Summary Sheet

- Pull each section's sub-total via a cross-sheet reference, e.g. ='BOQ - Civil'!F10, rather than retyping the number.

- Total Bid Price (excl. GST): =SUM() of the four section sub-totals.

- GST amount: = Total Bid Price × GST rate (keep the GST % in its own editable cell, e.g. =TotalBidPrice*C2, so the rate can be updated without touching the formula).

- Grand Total (incl. GST): = Total Bid Price + GST amount.

### Rate Analysis Sheet (per item, e.g. RCC M25)

- Material Sub-Total: =SUM() of each material line's Qty × Rate, uplifted by the wastage % in a separate cell, e.g. =SUM(D5:D9)*(1+$C$2).

- Direct Cost Sub-Total: = Material Sub-Total + Labour Sub-Total + Equipment Sub-Total.

- Analyzed Rate: = Direct Cost Sub-Total × (1 + Overheads%) × (1 + Contingency%) × (1 + Profit%), or additively if the Employer's own rate-analysis convention requires simple addition rather than compounding — confirm which convention the specific tender/organization uses.

- Link this Analyzed Rate cell directly into the corresponding BOQ tab's Unit Rate cell (e.g. ='Rate Analysis'!$G$20) so that any change to material/labour cost automatically re-prices the BOQ — do this only in the internal working copy, then paste values into the client-facing BOQ before submission if the Employer's format requires static numbers.

### Compliance & Statutory Checklist Sheets

- Use a data-validation dropdown (Y/N) for the 'Complied' / 'Attached' columns.

- A simple =COUNTIF(range,"N") cell at the top of the sheet gives an instant count of outstanding items before submission.

How to use this section: Build the internal (Rate Analysis, Compliance Checklist, Statutory Checklist) and client-facing workbooks as two separate files from the start, even though the content maps 1:1 to this single document — this avoids the single most common and costly mistake in Indian tendering: accidentally leaving an internal rate-analysis or margin sheet inside the file uploaded to the e-procurement portal.

# Appendix A — Glossary of Common Indian Tendering Terms

| Term | Meaning |
| --- | --- |
| NIT | Notice Inviting Tender — the public notice/document inviting bids |
| ITB | Instructions to Bidders — the section of tender documents governing bid preparation & submission procedure |
| GCC | General Conditions of Contract — the Employer's standard contract terms applicable across all its works |
| SCC | Special Conditions of Contract — project-specific amendments/additions to the GCC |
| EMD | Earnest Money Deposit — bid security submitted with the bid to demonstrate seriousness of intent |
| LOA | Letter of Acceptance — the Employer's formal acceptance of the successful bidder's offer |
| BOQ | Bill of Quantities — the itemized, priced schedule of work quantities and rates |
| TEC | Tender Evaluation Committee — the Employer's panel that evaluates Technical and Financial bids |
| DLP | Defects Liability Period — the post-completion period during which the contractor must rectify defects |
| RA Bill / IPC | Running Account Bill / Interim Payment Certificate — periodic progress-payment claims |
| EOT | Extension of Time — a formal extension to the contractual completion date |
| LD | Liquidated Damages — pre-agreed damages for contractor-caused delay |
| DSC | Digital Signature Certificate — required to sign and submit bids on Indian e-procurement portals |
| GeM / CPPP | Government e-Marketplace / Central Public Procurement Portal — common Indian e-tendering platforms |

# Appendix B — Typical Employers / Authorities in the Indian Market

- CPWD (Central Public Works Department) — central government civil works

- State PWD (Public Works Department) — state government civil/road works

- NHAI (National Highways Authority of India) — national highway infrastructure

- Metro Rail Corporations (DMRC, MMRC, BMRCL, etc.) — urban rail infrastructure

- Smart City SPVs (Special Purpose Vehicles) — city-level infrastructure & area development

- Municipal Corporations / Development Authorities — local civic infrastructure

- Private developers & REITs — residential, commercial and mixed-use real estate

- Industrial / institutional clients — factories, warehouses, hospitals, educational campuses

# Appendix C — Common Disqualification Reasons in Indian Tenders

- Technical bid contains commercial/price information (violates two-envelope sealing rules)

- EMD/Bid Security not in the prescribed instrument, amount, or validity period

- Missing or expired statutory registration (GST, PAN, MSME/Udyam, labour license)

- Bidder does not meet minimum average annual turnover or similar-work experience criteria

- BOQ item structure, description, or quantity altered from the Employer's issued format

- Arithmetic errors between quoted rate, quantity and amount in the Financial Bid

- Bid not digitally signed with a valid DSC, or uploaded after the portal deadline

- Conditional bid — bidder adds terms/conditions not permitted by the NIT

- Non-submission of a mandatory undertaking, affidavit, or Power of Attorney

- Bidder found blacklisted/debarred by any listed authority at the time of bid evaluation